## req_tasks
Task ID	Description	Estimated Time (Days)
TC1000	Power Supply voltage should be from 5V to 24V / 1. Reverse Polarity protection / 2. Over voltage protection (30V). / 3. Power supply indicator LED. / 4. Over Voltage indicator LED. / 5. The ground of Timer is same as provided reference ground.	5
TC2000	Output / 1. ON condition → Source Current / 2. OFF Condition → High Impedance / 3. Protected from solenoid high voltage spikes. / 4. Indicator LED when output is ON.	5
TC3000	Design an input capture unit. / 1. input is considered as high if voltage is above 1V. / 2. 20% hysteresis. / 3. Maximum input current should be below 50mA. / 4. The inputs are differential.	5
TC4000	Design the delays (3Nos) / 1. Adjustable by using trim pots. / 2. Adjustment range is 100ms to 5000ms.	5
TC5000	Design the mode selection / 1. A DIP Switch to change the mode. / 2. Mode1 : SET turn ON the output and RESET will turn if OFF. / 3. Mode2: SET turn ON the output and the hold timer will turn if OFF. RESET is ignored.	5
TC6000	Integrate the circuit and verify by simulation	5
TC7000	BOM Finalization	7
TC8000	PCB Design	15

	Total time	52

## user duties
Users Duties

1	Output to be NC or NO to be Decide by user. The circuit always provide current sink in ON and high impedance when OFF.
2	User needs to make sure about he input voltage supply. It should be in range for the need of solenoid valve.
3	The Power supply must be either floating or using same ground as provided as reference ground.

## risks
Task ID	a	m	b	te	var (b-a)/6^2
TC1000	2	5	10	5.3333	1.7778
TC2000	2	5	10	5.3333	1.7778
TC3000	2	5	10	5.3333	1.7778
TC4000	2	5	10	5.3333	1.7778
TC5000	2	5	10	5.3333	1.7778
TC6000	2	5	10	5.3333	1.7778
TC7000	2	7	14	7.3333	4.0000
TC8000	5	15	25	15.0000	11.1111
	TE	52		sum var	25.7777777777778

	Ts	Z	P(%)
	40	-2.36351579147501	0.905122757473112
	45	-1.37871754502709	8.39909289160172
	50	-0.393919298579168	34.6820310891879
	55	0.590878947868752	72.2699233753305
	60	1.57567719431667	94.2449892083715
	65	2.56047544076459	99.4773547436151
	70	3.54527368721251	99.980389718886